## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK11 | WEEK12 | WEEK13 | SPRINT REVIEW
User Story home page | 8
Mock-up of front-end |  |  |  | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0
test cases (test functionalities of buttons, display layout) |  |  |  | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 1 | 0 | 0
Design background style (CSS) |  |  |  | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Create main page layout (Html, CSS) |  |  |  | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Create the rental form for customer including CSS |  |  |  | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Write welcome information (special deals) and basic button functionalities |  |  |  | 8.5 | 5 | 2 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0
Verify story is completed (acceptance test) |  |  |  | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0.5
Wesbite Account | 13
Mock-up of front-end |  |  |  | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
test cases (check database saves entries correctly, check validation, ensure normalized, test scripts) |  |  |  | 8 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Create initial database |  |  |  | 6 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create table for employee and customer account detail (Mysql) |  |  |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create main page layout (CSS) |  |  |  | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create the login page and sign up page |  |  |  | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add the information of employee and customer to database |  |  |  | 6 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Check the username existed or not |  |  |  | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Add the JavaScript code for validations |  |  |  | 11 | 0 | 0 | 0 | 6 | 5 | 0 | 0 | 0 | 0
Add the input validations (onchange(), onblur()) |  |  |  | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Encrypt data in database |  |  |  | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Verify the login information |  |  |  | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Decrypt the password |  |  |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add the error message if login fail |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
Verify story is completed (acceptance test) |  |  |  | 5 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Persistent Menu Bar | 5 | bar: WEEK 6 to WEEK11
Mock-up of front-end |  |  |  | 2 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 1 | 0 | 0
Test case (menu bar remains persistent) |  |  |  | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Link buttons on menu bar to other parts of site |  |  |  | 4 | 0 | 0 | 1 | 1 | 1 | 0 | 3 | 0 | 0
Verify story is complete |  |  |  | 1 | 0 | 0 | 0.5 | 0 | 0 | 0 | 1 | 0 | 0
Role Authority | 13
Mock-up of front-end |  |  |  | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0
Test Case (different role can see different data) 2 |  |  |  | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
Create the staff information page layout |  |  |  | 3 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0
Create table to store staff information like position |  |  |  | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0
Display the staff information data in the staff information page |  |  |  | 7 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 0 | 0
Add the data fields to update the staff’s position |  |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0
Check if the input username existed or not |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0
Display the error message if the input username existed or not |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
Different role can see the different data |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0
Link the staff information page to other pag3 |  |  |  | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
Verify story is completed (acceptance test) |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Customer Recommendation | 3
mock up front end |  |  |  | 2 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0.5 | 0 | 0
Create the customer recommendation layout (CSS) |  |  |  | 5 | 0 | 0 | 1 | 2 | 1 | 1 | 0 | 0 | 1
Search by the year, month and city |  |  |  | 3 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0
Fetch the most popular car based on the year, month and city |  |  |  | 4 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1
Display the data from back-end to front-end |  |  |  | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Write test cases (ensure user has logged in, ensure location is correct, ensure top 10 cars are automatically displayed) |  |  |  | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Verify story is completed (acceptance test) |  |  |  | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
Contact Service | 5
Mock-up of front-end |  |  |  | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0
Test case (Contact detail shows in the form correctly) |  |  |  | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
Create the contact service page layout (CSS) |  |  |  | 3 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0
Create table to store employee’s contact detail |  |  |  | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
Create form |  |  |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Display contact detail in the form |  |  |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Verify story is completed (acceptance test) |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
Create new order | 5
Mock-up of front-end |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
Test case (Insert new order successfully) |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
Create the data fields in the order overview page |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0
Write the JS code to make sure the input validations |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 0 | 0
Check if the order id existed or not |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
Display the error message |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
Display the new order information in the order overview page |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
Verify story is completed (acceptance test) |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Managerial Analytics | 13
Mock-up of front-end |  |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0
Test case (normalization) |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
Create the order overview page layout (CSS) |  |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0
Create the order overview page (html) |  |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0
Create the database for all the data |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0
Display order in the form |  |  |  | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 1
Add “Fix Bug” button to eliminate incomplete data |  |  |  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 1
Verify story is completed (acceptance test) |  |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Manipulate Data | 21
mock up front end |  |  |  | 5 | 0 | 0 | 1.5 | 1 | 1 | 1 | 0.5 | 0 | 0
test cases (ensure data is pulled correctly from database by populating with data, check sort button functionality) |  |  |  | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 1
Create the monthly outcome page (html) |  |  |  | 6 | 0 | 0 | 2 | 1 | 2 | 0 | 1 | 0 | 0
Create the monthly outcome page layout (CSS) |  |  |  | 9 | 0 | 1 | 2 | 1 | 1 | 2 | 1 | 0 | 1
Add year and month button for sql queries |  |  |  | 3 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0
Get user’s input from the front-end |  |  |  | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0
Create the table for all the monthly outcome |  |  |  | 14 | 0 | 0 | 4 | 4 | 4 | 2 | 0 | 0 | 0
Write the query to fetch data based on year and month |  |  |  | 8 | 0 | 0 | 2 | 3 | 3 | 0 | 0 | 0 | 1
Write the query to count the number of pickup and return based on year and month |  |  |  | 10 | 1 | 1 | 2 | 2 | 3 | 1 | 0 | 0 | 0
Write the query to add the new column for the number of pickup and return |  |  |  | 9 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 1
Write the query to manage the data ordered by order id |  |  |  | 5 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1
Display the data the user would like to check from back-end to front-end |  |  |  | 11 | 0 | 0 | 5 | 4 | 0 | 0 | 2 | 0 | 0
Display the year, month and total order this month |  |  |  | 6 | 0 | 0 | 1 | 1 | 1 | 2 | 1 | 0 | 1
Add the login and logout function |  |  |  | 7 | 0 | 0 | 1 | 2 | 3 | 0 | 1 | 0 | 0
Display the user’s name on the page |  |  |  | 9 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 0 | 2
Verify story is completed (acceptance test) |  |  |  | 5 | 0 | 0 | 2 | 1 | 1 | 1 | 0 | 0 | 0
TOTAL |  |  |  | 399.5 | 65.5 | 29 | 46.5 | 42 | 56 | 62 | 72 | 16 | 15.5
TOTAL-REST |  |  |  | 399.5 | 334 | 305 | 258.5 | 216.5 | 160.5 | 98.5 | 26.5 | 10.5 | -5
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.